## Sheet1
S.no | Work Detail | Owner | Branch Name | Status | Merged
1 | State drop down | Vinay | feature/branch -name | Inprogress
2 | city (based on state) | Vinay |  | Inprogress
3 | if city is not existing then provide other option in city drop down and text box to enter city | Vinay |  | Inprogress
4 | add locality drop down | Vinay |  | Inprogress
5 | image compresssion in edit property | Vinay |  | Inprogress
6 | image delete option in edit proprety, ismain option should be updated | Vinay |  | Inprogress
7 | update edit properyt api which can handle ismain option | Manas |  | Inprogress
8 | images are not changing through thumbnail | Rishi |  | Inprogress
9 | society,locality,city,state in search box | Subhash | feature/small-changes | Done | Yes
10 | Notification api | manas |  | Inprogress
11 | Map location | Rishi |  | Inprogress
12 | location table | Ankit |  | Inprogress
13 | commercial and shop in nav bar and search bar tab | Ankit |  | Inprogress
14 | buy and rent button in navbar is not working | Rishi |  | Inprogress
15 | price slider in filter at both ends | vinay |  | Inprogress
16 | buy and rent page background change | Ankit |  | Inprogress
17 | Advance filter me Sell ke liye, availability and tenant preference remove krna hai | Rishi |  | Inprogress
18 | in post property , in amenty select only one out of fully furnieshed, semi furnished and unfurnished | Vinay |  | Inprogress
19 | Gas pipeline add in amenity table | Subhash | feature/small-changes | Done | Yes
20 | show name in profile | Rishi |  | Inprogress
21 | IsDeleted and ViewedContact column in Account table | Subhash | NA | Done | NA
22 | Normal usertype addition in Usertype table | Subhash | NA | Done | NA
23 | Prefill usertype in post property page as per usertype selected during sign up | Vinay
24 | creadetDt of property in getproperty api to show listed dated of a property | Manas | NA |  | NA
24 | Profile--> manage Account --2 drop down for Delete/Deactivate account, confirmation opoup on both cases | Rishi
25 | comment email in property details | Subhash | feature/email-comment-otherchanges | Done | yes
26 | Toggle for view contact --Enable toggle--View Contact Api call | Rishi
27 | Logout --clear Cache from local and storage -- clear token stored | Vinay