## Sheet1
S.no | Post property | owner | branch | Status
1 | State drop down | Vinay | feature/branch -name | Inprogress
2 | city (based on state) | Vinay |  | Inprogress
3 | if city is not existing then provide other option in city drop down and text box to enter city | Vinay |  | Inprogress
4 | add locality drop down | Vinay |  | Inprogress
5 | image compresssion in edit property | Vinay |  | Inprogress
6 | image delete option in edit proprety, ismain option should be updated | Vinay |  | Inprogress
7 | update edit properyt api which can handle ismain option | Manas |  | Inprogress
8 | images are not changing through thumbnail | Rishi |  | Inprogress
9 | society,locality,city,state in search box | Subhash |  | Inprogress
10 | Notification api | manas |  | Inprogress
11 | Map location | Rishi |  | Inprogress
12 | location table | Ankit |  | Inprogress
13 | commercial and shop in nav bar and search bar tab | Ankit |  | Inprogress
14 | buy and rent button in navbar is not working | Rishi |  | Inprogress
15 | price slider in filter at both ends | vinay |  | Inprogress
16 | buy and rent page background change | Ankit |  | Inprogress
17 | Advance filter me Sell ke liye, availability and tenant preference remove krna hai | Rishi |  | Inprogress
18 | in post property , in amenty select only one out of fully furnieshed, semi furnished and unfurnished | Vinay |  | Inprogress
19 | Gas pipeline add in amenity table | Subhash |  | Inprogress
20 | show name in profile | Subhash |  | Inprogress